## TEST SCENARIO
Test Scenerio Report
Project Name:- TUTORIALS NINJA URL: https://tutorialsninja.com/demo/ Tester: Prince Kumar Sarswat Date: 18-01-2025
Test Scenario ID | Test Scenario Description | Module | Priority | Version
TS-001 | Home page testing | Home page | High | Testing version on Netlify
TS-002 | product categories testing | products | High | Testing version on Netlify
TS-003 | Product page testing | products | High | Testing version on Netlify
TS-004 | page load speed | performance testing | high | Testing version on Netlify
TS-005 | stress testing | performance testing | high | Testing version on Netlify
TS-006 | login security and data protection | security testing | high | Testing version on Netlify
TS-007 | cross browser compatibility | browser/OS testing | high | Testing version on Netlify
TS-008 | verify the web application working properly in mobile like android and ios | mobile responsiveness testing | high | Testing version on Netlify
TS-009 | verify user can search the product with search bar | search | low | Testing version on Netlify
TS-010 | verify to add/remove products in wishlist | wishlist | low | Testing version on Netlify
TS-011 | shopping cart after adding something | shopping cart | low | Testing version on Netlify
TS-012 | verigy user can go on main page if click on Official logo | logo | high | Testing version on Netlify
TS-013 | verigy user can go for the support system | support | high | Testing version on Netlify
TS-014 | verify user can't go to the corporate without valid credentials | corporate | high | Testing version on Netlify
TS-015 | verify user can explore product | other menu | high | Testing version on Netlify
TS-016 | vefify user can explore watch section | watches | high | Testing version on Netlify
TS-017 | verify user can explore electronic musical instruments section | electronic musical instruments | high | Testing version on Netlify
TS-018 | verify user can explore calculators section | calculators | high | Testing version on Netlify
TS-019 | verigy user can explore label printers & others section | label printers & others | high | Testing version on Netlify
TS-020 | verigy user can redirects to products that is shown in the images on homepage or dashbord | dashbord images | high | Testing version on Netlify
TS-021 | vefigy user can go to the topics that is shown in homepage | topics | low | Testing version on Netlify
TS-022 | verify user can explore product catogerys | product category | low | Testing version on Netlify
TS-023 | verify user can get help by clickin on need help button | need help | high | Testing version on Netlify
TS-024 | vefigy user can go to the social media of the web plateform | social media logo | low | Testing version on Netlify
TS-025 | verify user can read company's copyright policys | copyrights | low | Testing version on Netlify
TS-026 | verigy user can read company's privacy policys and other policyes | policies | low | Testing version on Netlify
TS-027 | verify user can login | login | high | Testing version on Netlify
TS-028 | verify user can login with invalid credentials | login | high | Testing version on Netlify
TS-029 | verify user can sign in | sign in | high | Testing version on Netlify
TS-030 | verify user can sign in with invalid credentials | sign in | high | Testing version on Netlify
TS-031 | Paymet gateway and validation | payment module | high | Testing version on Netlify
TS-032
TS-033
TS-034

## TEST CASE
TEST CASE REPORT
Project Name:- TUTORIALS NINJA URL: https://tutorialsninja.com/demo/ Tester: Prince Kumar Sarswat Date: 18-01-2025+A2:J14
Test Case ID | Test Case Scenario Id | Test Case Description | Preconditions | Test Steps | Expected Result | Actual Result | Status | Priority | Comments
TC-001 | TS-001 | Verify the home page is displayed correctly. | User is on homepage. | 1. Navigate to the homepage. 2. Verify all elements are functional. | Homepage displays correctly. | Homepage displays correctly. | Passed | High
TC-002 | TS-002 | Verify product categories are displayed on the product page. | User is on homepage. | 1. Navigate to product page. 2. Verify product categories are displayed. | Product categories displayed. | Product categories displayed. | Passed | High
TC-003 | TS-003 | Verify product page load time is within the acceptable limit. | User is on homepage. | 1. Navigate to product page. 2. Measure load time. | Page load time within 2 seconds. | Page load time within 2 seconds. | Passed | High
TC-004 | TS-004 | Verify for all functionality load time is within the acceptable limit. | User is on homepage. | 1. Navigate to product page. 2. Measure load time. | Page load time within 2 seconds. | Page load time within 2 seconds. | Passed | High
TC-005 | TS-005 | Verify the search functionality works correctly. | User is on homepage. | 1. Use search bar. 2. Verify correct results. | Relevant search results. | Not showing results | Failed | High
TC-006 | TS-006 | Verify wishlist functionality works. | User is on product page. | 1. Click 'Add to Wishlist'. 2. Verify success message. | Product added to wishlist. | Wishlist not working properly in the home page, we have to go for the categery and then can see our wishlist | Passed | High | Wishlist not working properly in the home page, we have to go for the categery and then can see our wishlist
TC-007 | TS-007 | Verify cross-browser compatibility of the site. | User is on homepage. | 1. Open site in different browsers. 2. Verify layout and functionality. | All browsers show consistent functionality. | All browsers show consistent functionality. | Passed | Low
TC-008 | TS-008 | verify user can browse with android | Androide Phone | 1. Open site in different browsers. 2. Verify layout and functionality. | All devices show consistent functionality. | All devices show consistent functionality. | Passed | Low
TC-009 | TS-009 | Verify the search functionality works correctly. | User is on homepage. | 1. Use search bar. 2. Verify correct results. | Relevant search results. | Not showing results | Failed | High
TC-010 | TS-010 | Verify user can view their wishlist items after login. | User is logged in. | 1. Add items to wishlist. 2. Verify wishlist after login. | Wishlist items shown. | login module is not there, but still we can add product to wishlist but on the same time we can see them after the session time out we can’t see them and also not in other device | Failed | High
TC-011 | TS-011 | Verify shopping cart functionality after adding a product. | User is on shopping cart page. | 1. Add product to cart. 2. Verify cart is updated. | Product added to cart. | Add to cart button is not there | Failed | High | Add to cart button should be there as if a user wants to buy two or more product at same time
TC-012 | TS-012 | Verify the logo link redirects to the homepage. | User is on homepage. | 1. Click on logo. 2. Verify redirection to homepage. | Homepage loaded. | Not showing results | Failed | High | when user is on other page of websit and wants to go on home page the logo of website should redirects to them to the home page
TC-013 | TS-013 | Verify the support page is accessible. | User is logged in. | 1. Navigate to support page. 2. Verify accessibility. | Support page accessible. | Support page is not accessible as the button redirects to the same page | Failed | High | if user have any problems or doubts there should be active support sys to resolve concerns
TC-014 | TS-014 | Verify the corporate page is accessible with a valid request. | User has valid access. | 1. Navigate to corporate page. 2. Verify valid page load. | Corporate page loads with valid request. | Corporate page is not working and redirects to the same page | Failed | High | corporate page should be accessible to the employees and officail staff of the company with a valid credentials
TC-015 | TS-015 | Verify user can explore the topics section. | User is logged in. | 1. Navigate to topics. 2. Verify all sections load. | Topics section accessible. | Topics section is accessible but the information they are contaning not redirecting to the product | Failed | High
TC-016 | TS-016 | Verify watches section works properly | User is logged in. | 1. Navigate to watches section. 2. Verify product view. | Watches section works. | Watches section works. | Passed | High
TC-017 | TS-017 | Verify the musical instruments section for product view. | User is logged in. | 1. Navigate to musical instruments section. 2. Verify product view. | Musical instruments section works. | Musical instruments section works. | Passed | High
TC-018 | TS-018 | Verify calculator section for product view and favorites. | User is logged in. | 1. Navigate to calculators section. 2. Verify product view. | Calculators section works. | Calculators section works. | Passed | High
TC-019 | TS-019 | Verify the label printers section for product view. | User is logged in. | 1. Navigate to label printers section. 2. Verify product view. | Label printers section works. | Label printers section works. | Passed | High
TC-020 | TS-020 | Verify dashboard images are displayed correctly. | User is logged in. | 1. Verify dashboard images load. 2. Check for any broken links. | Dashboard images load. | Dashboard images loading but not redirecting to the product or the detials that is showing | Failed | High | from the dashboard images, if users wants to get more details or the detaild product overview they should be redirected to the product that is shown
TC-021 | TS-021 | Verify privacy policy page is accessible. | User is logged in. | 1. Navigate to privacy policy page. 2. Verify load. | Privacy policy page loads. | privacy policy page is not redirecting to the information and redirecting to the same page | Failed | Low
TC-022 | TS-022 | Verify product categories navigation works. | User is logged in. | 1. Navigate to categories. 2. Verify redirection. | Product categories navigated. | Product categories navigated. | Passed | High
TC-023 | TS-023 | Verify the Need Help button functionality. | User is logged in. | 1. Click on Need Help. 2. Verify support form loads. | Support form loads. | Need help button is not working and redirecting to the same page | Failed | High
TC-024 | TS-024 | Verify social media logo links redirect to the appropriate site. | User is logged in. | 1. Click on social media logos. 2. Verify redirection. | Redirect to correct social site. | logo is not workable or redirecting to the social plateform | Failed | Low
TC-025 | TS-025 | Verify copyrights page is accessible. | User is logged in. | 1. Navigate to copyright page. 2. Verify load. | Copyright page loads. | copyright page is not redirecting to the information and redirecting to the same page | Failed | Low
TC-026 | TS-026 | Verify terms of use page is accessible. | User is logged in. | 1. Navigate to terms of use page. 2. Verify load. | Terms of use page loads. | Terms and condition page is not redirecting to the information and redirecting to the same page | Failed | Low
TC-027 | TS-027 | Verify user can sign up and log in. | User is logged in. | 1. Click sign up. 2. Enter details and verify login. | Login successful. | There is no any option for that and can't login and signup | Failed | High
TC-028 | TS-028
TC-029 | TS-029
TC-030 | TS-030
TC-031 | TS-031
TC-032 | TS-032
TC-033 | TS-033
TC-034 | TS-034
TC-035 | TS-035
TC-036 | TS-036
TC-037 | TS-037

## TEST EXECUTION
Test Execution Report
Project Name:- TUTORIALS NINJA URL: https://tutorialsninja.com/demo/ Tester: Prince Kumar Sarswat Date: 18-01-2025
Test Case ID | Test Scenario | Module | Test Case Description | Tester | Execution Date | Status | Comments
TC-001 | TS-001 | Home page | Verify the home page is displayed correctly. | Prince Kumar Sarswat | 2025-01-18 | Passed
TC-002 | TS-002 | products | Verify product categories are displayed on the product page. | Prince Kumar Sarswat | 2025-01-18 | Passed
TC-003 | TS-003 | products | Verify product page load time is within the acceptable limit. | Prince Kumar Sarswat | 2025-01-18 | Passed
TC-004 | TS-004 | performance testing | Verify for all functionality load time is within the acceptable limit. | Prince Kumar Sarswat | 2025-01-18 | Passed
TC-005 | TS-005 | performance testing | Verify the search functionality works correctly. | Prince Kumar Sarswat | 2025-01-18 | Failed
TC-006 | TS-006 | wishlist | Verify wishlist functionality works. | Prince Kumar Sarswat | 2025-01-18 | Passed | Wishlist not working properly in the home page, we have to go for the categery and then can see our wishlist
TC-007 | TS-007 | browser/OS testing | Verify cross-browser compatibility of the site. | Prince Kumar Sarswat | 2025-01-18 | Passed
TC-008 | TS-008 | mobile responsiveness testing | verify user can browse with android | Prince Kumar Sarswat | 2025-01-18 | Passed
TC-009 | TS-009 | search | Verify the search functionality works correctly. | Prince Kumar Sarswat | 2025-01-18 | Failed
TC-010 | TS-010 | wishlist | Verify user can view their wishlist items after login. | Prince Kumar Sarswat | 2025-01-18 | Failed
TC-011 | TS-011 | shopping cart | Verify shopping cart functionality after adding a product. | Prince Kumar Sarswat | 2025-01-18 | Failed | Add to cart button should be there as if a user wants to buy two or more product at same time
TC-012 | TS-012 | logo | Verify the logo link redirects to the homepage. | Prince Kumar Sarswat | 2025-01-18 | Failed | when user is on other page of websit and wants to go on home page the logo of website should redirects to them to the home page
TC-013 | TS-013 | support | Verify the support page is accessible. | Prince Kumar Sarswat | 2025-01-18 | Failed | if user have any problems or doubts there should be active support sys to resolve concerns
TC-014 | TS-014 | corporate | Verify the corporate page is accessible with a valid request. | Prince Kumar Sarswat | 2025-01-18 | Failed | corporate page should be accessible to the employees and officail staff of the company with a valid credentials
TC-015 | TS-015 | other menu | Verify user can explore the topics section. | Prince Kumar Sarswat | 2025-01-18 | Failed
TC-016 | TS-016 | watches | Verify watches section works properly | Prince Kumar Sarswat | 2025-01-18 | Passed
TC-017 | TS-017 | electronic musical instruments | Verify the musical instruments section for product view. | Prince Kumar Sarswat | 2025-01-18 | Passed
TC-018 | TS-018 | calculators | Verify calculator section for product view and favorites. | Prince Kumar Sarswat | 2025-01-18 | Passed
TC-019 | TS-019 | label printers & others | Verify the label printers section for product view. | Prince Kumar Sarswat | 2025-01-18 | Passed
TC-020 | TS-020 | dashbord images | Verify dashboard images are displayed correctly. | Prince Kumar Sarswat | 2025-01-18 | Failed | from the dashboard images, if users wants to get more details or the detaild product overview they should be redirected to the product that is shown
TC-021 | TS-021 | topics | Verify privacy policy page is accessible. | Prince Kumar Sarswat | 2025-01-18 | Failed
TC-022 | TS-022 | product category | Verify product categories navigation works. | Prince Kumar Sarswat | 2025-01-18 | Passed
TC-023 | TS-023 | need help | Verify the Need Help button functionality. | Prince Kumar Sarswat | 2025-01-18 | Failed
TC-024 | TS-024 | social media logo | Verify social media logo links redirect to the appropriate site. | Prince Kumar Sarswat | 2025-01-18 | Failed
TC-025 | TS-025 | copyrights | Verify copyrights page is accessible. | Prince Kumar Sarswat | 2025-01-18 | Failed
TC-026 | TS-026 | policies | Verify terms of use page is accessible. | Prince Kumar Sarswat | 2025-01-18 | Failed
TC-027 | TS-027 | login | Verify user can sign up and log in. | Prince Kumar Sarswat | 2025-01-18 | Failed

## BUG REPORT
Defect Report
Project Name:- TUTORIALS NINJA URL: https://tutorialsninja.com/demo/ Tester: Prince Kumar Sarswat Date: 18-01-2025
Defect ID | Test Case ID | Test Scenario | Module | Test Case Description | Tester | Execution Date | Status | Comments | Priority/Severity | ScreenShot
DEF ID 001 | TC-005 | TS-005 | logo | Verify the logo link redirects to the homepage. And it is same as the website name or related so user can understand | Prince Kumar Sarswat | 2025-01-18 | Failed | logo is not as described name | Non Critical/High
DEF ID 002 | TC-009 | TS-009 | Contact Us | verify the contact us form sends a confirmation mail to the selected mail for inquery has made with this mail | Prince Kumar Sarswat | 2025-01-18 | Failed | email not received and no any confirmation on website | Non Critical/High
DEF ID 003 | TC-010 | TS-010 | Registration | verify new user ragistration with fake credentials | Prince Kumar Sarswat | 2025-01-18 | Failed | its should verify the email that is mentioned by OTP authentacion or other verification method | Critical/High
DEF ID 004 | TC-011 | TS-011 | Forgot Password | vefigy that forgot password page is working correctly | Prince Kumar Sarswat | 2025-01-18 | Failed | it should send a verification mail or the link to the mail to reset the password | Critical/High
DEF ID 005 | TC-012 | TS-012 | product Descriptions | Verify the description data is correct or good for the users | Prince Kumar Sarswat | 2025-01-18 | Failed | it is no up to the mark | Critical/High
DEF ID 006 | TC-013 | TS-013 | product category selection | verify products is added to cart after selecting category | Prince Kumar Sarswat | 2025-01-18 | Failed | no any selection category is there for buying the item not able to add to the cart | Critical/High
DEF ID 007 | TC-014 | TS-014 | Product comparision | Verify that the product comparision is showing the relative data | Prince Kumar Sarswat | 2025-01-18 | Failed | it is not showing the correct data it can lead to bussiness loss | Critical/High
DEF ID 008 | TC-015 | TS-015 | Chekout | Verify it is smooth process for payment and checkout | Prince Kumar Sarswat | 2025-01-18 | Failed | it is redirecting to the same page only | Critical/High
DEF ID 009 | TC-020 | TS-020 | Delievery date | verify that it is taking the availabe date or showing which date for the address can be taken | Prince Kumar Sarswat | 2025-01-18 | Failed | It should firstly on the wrong path there is clss for category there should be product category option then it is taking for the previous dates for delivery and don’t ask for the location and not showing up to mark results | Critical/High
DEF ID 010 | TC-021 | TS-021 | order status | verify it is showing all correct details | Prince Kumar Sarswat | 2025-01-18 | Failed | it is showing the wrong delivery dates and details | Critical/High
DEF ID 011 | TC-023 | TS-023 | order status | Verify the Need Help button functionality. | Prince Kumar Sarswat | 2025-01-18 | Failed | it is showing the wrong delivery dates and details | High
DEF ID 012 | TC-024 | TS-024 | order status | Verify the Need Help button functionality. | Prince Kumar Sarswat | 2025-01-18 | Failed | it is showing the wrong delivery dates and details | Low
DEF ID 013 | TC-025 | TS-025 | order status | Verify the Need Help button functionality. | Prince Kumar Sarswat | 2025-01-18 | Failed | it is showing the wrong delivery dates and details | Low
DEF ID 014 | TC-026 | TS-026 | order status | Verify the Need Help button functionality. | Prince Kumar Sarswat | 2025-01-18 | Failed | it is showing the wrong delivery dates and details | Low
DEF ID 015 | TC-027 | TS-027 | order status | Verify the Need Help button functionality. | Prince Kumar Sarswat | 2025-01-18 | Failed | it is showing the wrong delivery dates and details | High

## SUMMARY
Test Execution Overview
Total Test Cases Executed: | 27
Total Passed: | 12
Total Failed: | 15
Major Failures Identified:
Wishlist Page: Accessibility issue in the homepage.
Shopping Cart: Add to cart button missing.
Support System: No active support system for user issues.
Logo: Does not redirect to the homepage from other pages.
Corporate Page: Access issues for valid employees.
Need Help Button: Non-functional.
Social Media Logos: Incorrect redirection to external sites.
Login Issues: Problems in signing up and logging in.